## FunA_LauNgaSze
Task allocation (Function A)
Tasks | 1/5/2023 | 2/5/2023 | 3/5/2023 | 4/5/2023 | 5/5/2023 | 6/5/2023
Design function A logic | 6 | 3 | 2 | 0 | 0 | 0
Create and modify function A layout | 6 | 4 | 3 | 1 | 1 | 0
Develop and modify function A | 6 | 6 | 4 | 2 | 0 | 0
Write JX documentation | 6 | 6 | 6 | 4 | 2 | 0
Write unit test case | 6 | 6 | 6 | 4 | 3 | 0
Total working hours remaining | 30 | 25 | 21 | 11 | 6 | 0

## FunB_CheungKwokWai
Task allocation (Function B)
Tasks | 1/5/2023 | 2/5/2023 | 3/5/2023 | 4/5/2023 | 5/5/2023 | 6/5/2023
Design function B logic | 6 | 3 | 0 | 0 | 0 | 0
Create and modify function B layout | 6 | 4 | 2 | 0 | 0 | 0
Develop and modify function B | 6 | 5 | 3 | 2 | 0 | 0
Write JX documentation | 6 | 6 | 5 | 3 | 2 | 0
Write unit test case | 6 | 6 | 6 | 4 | 2 | 0
Total working hours remaining | 30 | 24 | 16 | 9 | 4 | 0

## FunC_LeeChunYin
Task allocation (Function C)
Tasks | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 1/5/2023 | 2/5/2023 | 3/5/2023 | 4/5/2023 | 5/5/2023 | 6/5/2023
Design function C logic | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create and modify function C layout | 6 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Develop and modify function C | 6 | 6 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Write JX documentation | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 1 | 0 | 0 | 0
Write unit test case | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 2 | 1 | 0
Total working hours remaining | 30 | 24 | 20 | 18 | 15 | 10 | 8 | 4 | 2 | 1 | 0